## SprintSheet
|  |  |  | Week #1 |  |  | Week #2 |  |  | Week #3 |  |  | Week #4 |  |  | Week #5 |  |  | Week #6 |  |  | Week #7 |  |  | Week #8 |  |  | Week #9 |  |  | Week #10
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint hrs = 224) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30
|  |  |  | 2020-03-02 | 2020-03-04 | 2020-03-06 | 2020-03-09 | 2020-03-11 | 2020-03-12 | 2020-03-16 | 2020-03-17 | 2020-03-20 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-28 | 2020-04-29 | 2020-05-03
|  |  |  | 224 | 217 | 209 | 201 | 193 | 185 | 177 | 169 | 161 | 153 | 145 | 137 | 129 | 121 | 113 | 105 | 97 | 89 | 81 | 73 | 65 | 57 | 49 | 41 | 33 | 25 | 17 | 9 | 1 | 0 | Ideal Burndown
|  |  | 224 | 218 | 212 | 208 | 200 | 195 | 190 | 178 | 171 | 166 | 158 | 151 | 145 | 140 | 127 | 121 | 114 | 101 | 97 | 88 | 81 | 73 | 64 | 58 | 49 | 44 | 31 | 25 | 13 | 2 | 0 | Remaining hrs (Total)
Requirement Gathering | gothrough and understand the requirements | Rashmi | 4 | 2020-03-02: 2; 2020-03-06: 2
| gothrough and understand the requirements | Juhi | 4 | 2020-03-04: 4
| gothrough and understand the requirements | Shubham | 4 | 2020-03-02: 1; 2020-03-04: 1; 2020-03-06: 2
| gothrough and understand the requirements | Darshan | 4 | 2020-03-02: 3; 2020-03-04: 1
Project Initial Phase | UI Wireframes | Rashmi | 4 | 2020-03-12: 4
| Architecture Diagram | Juhi | 4 | 2020-03-09: 4
| Code Setup with our Tech Stack | Shubham | 4 | 2020-03-09: 2; 2020-03-11: 3; 2020-03-12: 1
| XP core value implementation | Darshan | 4 | 2020-03-09: 2; 2020-03-11: 2
Project discussion | Discuss design pattern | Rashmi | 6 | 2020-03-16: 3; 2020-03-17: 3
| Discussion & weekly scrum task board/sheet | Juhi | 6 | 2020-03-16: 2; 2020-03-17: 2; 2020-03-20: 2
| Discuss application flow | Shubham | 6 | 2020-03-16: 4; 2020-03-20: 2
| Discussion & create weekly scrum report | Darshan | 6 | 2020-03-16: 3; 2020-03-17: 2; 2020-03-20: 1
Development and Testing | Handle Registartion | Rashmi | 6 | 2020-03-23: 5
| Create database | Juhi | 6 | 2020-03-24: 4
| Handle Memebership verification | Shubham | 6 | 2020-03-25: 6
| Handle login | Darshan | 6 | 2020-03-23: 3; 2020-03-24: 3
| Backend implementationf for User registartion | Rashmi | 6 | 2020-03-31: 3; 2020-04-01: 3
| Created related database architecture | Juhi | 6 | 2020-04-01: 6
| Backend implementation for Membership | Shubham | 6 | 2020-03-31: 2; 2020-04-01: 2; 2020-04-02: 2
| Backend implementation for User Login | Darshan | 6 | 2020-04-01: 2; 2020-04-02: 4
| Handle Admin functionality | Rashmi | 6 | 2020-04-03: 2; 2020-04-07: 2; 2020-04-08: 2
| Handle Database | Juhi | 6 | 2020-04-03: 2; 2020-04-07: 4
| Handle Membership renew | Shubham | 6 | 2020-04-07: 4; 2020-04-08: 2
| Handle Admin login | Darshan | 6 | 2020-04-03: 3; 2020-04-07: 3
| Backend/API implementation for VehicleDetails | Rashmi | 6 | 2020-04-09: 4; 2020-04-10: 2
| Handle Database, write test cases | Juhi | 6 | 2020-04-11: 6
| Backend/API implementation for Membership renew | Shubham | 6 | 2020-04-09: 3; 2020-04-10: 3
| Backend implementation for Admin login. Unit testing | Darshan | 6 | 2020-04-09: 2; 2020-04-10: 2; 2020-04-11: 2
| Handle car Search and terminate user | Rashmi | 6 | 2020-04-14: 2; 2020-04-15: 2; 2020-04-16: 2
| Handle database backup | Juhi | 6 | 2020-04-14: 4; 2020-04-15: 2
| Handle Car Booking | Shubham | 6 | 2020-04-15: 1; 2020-04-16: 5
| Handle Booking cancellation and end membership | Darshan | 6 | 2020-04-14: 3; 2020-04-15: 1; 2020-04-16: 2
| Create setup for deployment. Tetsing | Rashmi | 6 | 2020-04-20: 1; 2020-04-21: 3; 2020-04-22: 2
| Perform final testing | Juhi | 6 | 2020-04-20: 3; 2020-04-21: 3
| Create setup for deployment. Tetsing | Shubham | 6 | 2020-04-20: 1; 2020-04-21: 3; 2020-04-22: 2
| Handle booking Cancellation implementaion | Darshan | 6 | 2020-04-21: 4; 2020-04-22: 2
Deployment, final testing and Project Handover | Deploy the application | Rashmi | 6 | 2020-04-28: 6
| Create final documentation,diagrams, scrum detail | Juhi | 6 | 2020-04-29: 5; 2020-05-03: 1
| Deploy the application | Shubham | 6 | 2020-04-28: 6
| Perform final testing and AWS config setup | Darshan | 6 | 2020-04-29: 6
Team:
Rashmi | 4-6 hrs / week
Juhi | 4-6 hrs / week
Shubham | 4-6 hrs / week
Darshan | 4-6 hrs / week
Total Available Hours During Sprint: | 224