## Sheet1
Week | Team Members | What tasks did I work on / complete? | What am I planning to work on next? | What tasks are blocked waiting on another team member?
1 | Rashmi | Requirement understanding | UI Wireframes | -
| Juhi | Requirement understanding | Architecture Diagram | -
| Darshan | Requirement understanding | XP core value implementation | -
| Shubham | Requirement understanding | Code Setup with our Tech Stack | -
2 | Rashmi | Created rough wireframes | Discuss design pattern | -
| Juhi | Created rough architecture diagram | Discussion & weekly scrum taskboard/sheet | -
| Darshan | suggested related XP core value for the team | Discuss application flow | -
| Shubham | did initial code setup | Discuss application flow | -
3 | Rashmi | Different Design pattern required for Nodejs | Handle Registration | -
| Juhi | Initiated weekly scrum task sheet | Create a database | -
| Darshan | discussed application initial flow | Handle Login | -
| Shubham | guided the team on initial code setup | Handle Membership verification | -
4 | Rashmi | Created Registration user Interface | Backend implementation for User registration | Database setup
| Juhi | Set up done for RDS on AWS | Created related database architecture | -
| Darshan | Created Login user Interface | Backend implementation for User Login | Database setup
| Shubham | Created Membership verification UI | Backend implementation for Membership | Database setup
5 | Rashmi | implemented backend for User Registration | Handle Admin functionality | Admin login setup
| Juhi | Database setup is done | Handle Database | -
| Darshan | implemented backend for User Login | Handle Admin login | -
| Shubham | implemented backend for Membership verification | Handle Membership renew | -
6 | Rashmi | Created UI for Admin to add vehicle details | Backend/API implementation for vehicle details | -
| Juhi | Database table and query created | Handle Database, write test cases | -
| Darshan | Admin login flow done | Backend implementation for Admin login. Unit testing | -
| Shubham | Created UI for Membership renew | Backend/API implementation for Membership renew | -
7 | Rashmi | Admin functionality implemented | Handle car Search and terminate the user | -
| Juhi | Database stored procedures, test cases created. | Handle database backup | -
| Darshan | Tests are successful. | Handle Booking cancellation and end membership | Car booking feature
| Shubham | Membership feature completed | Handle Car booking | -
8 | Rashmi | Admin feature completed. | Create setup for deployment. Testing | Booking cancellation
| Juhi | Database queries and functions completed | Perform final testing | Booking cancellation
| Darshan | End membership done. | Handle booking Cancellation implementation | -
| Shubham | Car booking done | Create a setup for deployment. Testing | Booking cancellation
9 | Rashmi | Deployment setup done. | Deploy the application | -
| Juhi | Tests are successful. | Create final documentation, diagrams, scrum detail | -
| Darshan | Cancel booking done | Perform final testing | -
| Shubham | Deployment setup done. | Deploy the application | -
10 | Rashmi | Application deployed successfully | - | -
| Juhi | Final testing performed | - | -
| Darshan | Final testing performed | - | -
| Shubham | Application deployed successfully | - | -